## Schedule_Data_Option_A
ID | WBS | Task | Phase | Owner | Start | End | Duration | Notes
MOB-001 | A0 | MOBILIZATION | MOBILIZATION | All | 2026-01-26 | 2026-02-05 | 10
SPM-001 | A0 | SPMT | BUFFER | All | 2026-01-26 | 2026-02-05 | 10
A1000 | A0 | Mobilization of 1st set of SPMT; Asembly + Function Test | MOBILIZATION | All | 2026-01-26 | 2026-01-26 12:00 | 0.5
A1010 | A0 | Mobilization of 2nd set of SPMT; Assembly + Function test | MOBILIZATION | All | 2026-02-04 | 2026-02-04 12:00 | 0.5
MAR-002 | A0 | MARINE | BUFFER | All | 2026-01-26 | 2026-01-26 | 0
A1001 | A0 | Mobilization of Marine Equipment and Steelworks | MOBILIZATION | All | 2026-01-26 | 2026-01-26 | 0
JAC-003 | A0 | JACKING EQUIPMENT, STEEL BRIDGE | BUFFER | All | 2026-01-29 | 2026-01-29 | 0
A2010 | A0 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!)) | MOBILIZATION | All | 2026-01-29 | 2026-01-30 | 1
MOB-001 | A0 | DEMOBILIZATION | MOBILIZATION | All | 2026-02-27 | 2026-03-09 | 10
SPM-004 | A0 | SPMT | BUFFER | All | 2026-02-27 | 2026-03-07 12:00 | 8.5
A1980 | A0 | Demobilization of 2nd set of SPMT | MOBILIZATION | All | 2026-02-27 | 2026-02-27 | 0
A1990 | A0 | Demobilization of 1st set of SPMT | MOBILIZATION | All | 2026-03-06 | 2026-03-06 | 0
MAR-005 | A0 | MARINE | BUFFER | All | 2026-03-08 | 2026-03-08 | 0
A2000 | A0 | Demobilization of Marine Equipment and Steelworks | MOBILIZATION | All | 2026-03-08 | 2026-03-08 | 0
JAC-006 | A0 | JACKING EQUIPMENT, STEEL BRIDGE | BUFFER | All | 2026-03-08 | 2026-03-08 | 0
A2020 | A0 | Demobilization of Jacking Equipment and Steel bridge | MOBILIZATION | All | 2026-03-08 | 2026-03-08 | 0
OPE-007 | A0 | OPERATIONAL | BUFFER | All | 2026-01-27 | 2026-03-08 | 40
BEA-008 | A0 | Beam Replacement | BUFFER | All | 2026-01-27 | 2026-02-25 | 29
A1002 | A0 | Beam Replacement AGI TR Unit 1 (TR Bay 4) - Two 5t forklifts required | BUFFER | All | 2026-01-27 | 2026-01-27 | 0
A1003 | A0 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required | BUFFER | All | 2026-01-28 | 2026-01-28 | 0
A1013 | A0 | Beam Replacement AGI TR Unit 3 (TR Bay 2) - Two 5t forklifts required | BUFFER | All | 2026-02-05 | 2026-02-05 | 0
A1023 | A0 | Beam Replacement AGI TR Unit 4 (TR Bay 1) - Two 5t forklifts required | BUFFER | All | 2026-02-06 | 2026-02-06 | 0
A1033 | A0 | Beam Replacement AGI TR Unit 5 (TR Bay 5) - Two 5t forklifts required | BUFFER | All | 2026-02-15 | 2026-02-15 | 0
A1043 | A0 | Beam Replacement AGI TR Unit 6 (TR Bay 6) - Two 5t forklifts required | BUFFER | All | 2026-02-16 | 2026-02-16 | 0
A1053 | A0 | Beam Replacement AGI TR Unit 7 (TR Bay 7) - Two 5t forklifts required | BUFFER | All | 2026-02-24 | 2026-02-24 | 0
PREP-001 | A0 | Deck Preparations | DECK_PREP | All | 2026-01-27 | 2026-01-29 | 2
A1004 | A0 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required | DECK_PREP | All | 2026-01-27 | 2026-01-27 | 0
A1005 | A0 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation | DECK_PREP | All | 2026-01-28 | 2026-01-28 | 0
AGI-009 | A0 | AGI TR Units 1-2 | BUFFER | All | 2026-01-29 | 2026-02-14 | 16
A1030 | A0 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | BUFFER | All | 2026-01-29 | 2026-01-29 07:12 | 0.3
A1040 | A0 | RoRo Ramp Installation - 5t Frokift and Crane required | BUFFER | All | 2026-01-29 | 2026-01-29 07:12 | 0.3
A1060 | A0 | Load-out of AGL TR Unit 1; stool down (10am-11am) | LOADOUT | All | 2026-01-29 | 2026-01-29 04:48 | 0.2
A1070 | A0 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required | SEAFAST | All | 2026-01-29 | 2026-01-29 | 0
A1071 | A0 | Loading of AGI TR Unit 2 on SPMT; lashing | BUFFER | All | 2026-01-29 | 2026-01-29 | 0
A1072 | A0 | Shifting of AGL TR Unit 2 to Jetty area | BUFFER | All | 2026-01-30 | 2026-01-30 01:12 | 0.05
A1073 | A0 | RoRo Ramp Installation - Crane required | BUFFER | All | 2026-01-30 | 2026-01-30 07:12 | 0.3
A1074 | A0 | Load-out of AGI TR Unit 2; stoold down; securing of SPMT (8am-9am) | LOADOUT | All | 2026-01-30 | 2026-01-30 07:12 | 0.3
A1075 | A0 | Removal of RoRo Ramp; Sea fastening AGI TR Unit 2 - Crane required | SEAFAST | All | 2026-01-30 | 2026-01-30 | 0
A1080 | A0 | MWS + MPI + Final Preparations | BUFFER | All | 2026-01-31 | 2026-01-31 04:48 | 0.2
A1081 | A0 | Sail-away - Marine Transportation by LCT to Al Ghallan Island | SAIL | All | 2026-02-01 | 2026-02-01 | 0
A1090 | A0 | MMT Crew Mob to AGI; Site Induction; Meeting with Client | BUFFER | All | 2026-02-02 | 2026-02-02 | 0
A1091 | A0 | LCT Arrival; Berthing at AGL RoRo Jetty | AGI_UNLOAD | All | 2026-02-02 | 2026-02-02 | 0
A1100 | A0 | Unlashing and cutting; steel sets preparations - Forklift required | BUFFER | All | 2026-02-02 | 2026-02-02 | 0
A1110 | A0 | Load-in of AGI TR Unit 2 (including RoRo Ramp Installation); store on Jetty - Crane required | LOADOUT | All | 2026-02-03 | 2026-02-03 | 0
A1120 | A0 | Load-in of AGI TR Unit 1 (including RoRo Ramp Installation); store on Jetty - Crane required | LOADOUT | All | 2026-02-04 | 2026-02-04 | 0
A1121 | A0 | LCT Sails back to MZP to collect TR Units 3-4 | SAIL | All | 2026-02-05 | 2026-02-05 | 0
A1122 | A0 | Steel bridge Installation 1 - Crane required | BUFFER | All | 2026-02-05 | 2026-02-05 07:12 | 0.3
A1140 | A0 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | BUFFER | All | 2026-02-05 | 2026-02-05 16:48 | 0.7
A1141 | A0 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required | TURNING | All | 2026-02-06 | 2026-02-06 | 0
A1150 | A0 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required | JACKDOWN | All | 2026-02-09 | 2026-02-09 | 0
A1160 | A0 | Steel bridge Installation 2 - Crane required | BUFFER | All | 2026-02-09 | 2026-02-09 07:12 | 0.3
A1170 | A0 | AGL TR Unit 2 (TR Bay 3) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | BUFFER | All | 2026-02-09 | 2026-02-09 16:48 | 0.7
A1180 | A0 | Turning of AGI TR Unit 2 (TR Bay 3) - 10t Forklift required | TURNING | All | 2026-02-10 | 2026-02-10 | 0
A1181 | A0 | SPMT shifting back to Port | BUFFER | All | 2026-02-11 | 2026-02-11 | 0
A1190 | A0 | Jacking down of AGI TR Unit 2 (TR Bay 3) on temporary support - Forklift and Crane required | JACKDOWN | All | 2026-02-13 | 2026-02-13 | 0
AGI-010 | A0 | AGI TR Units 3-4 | BUFFER | All | 2026-02-06 | 2026-02-23 | 17
A1200 | A0 | LCT arrives to MZP; Deck preparations | DECK_PREP | All | 2026-02-06 | 2026-02-06 | 0
A1210 | A0 | Loading of AGI TR Unit 3 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | BUFFER | All | 2026-02-07 | 2026-02-07 07:12 | 0.3
A1220 | A0 | RoRo Ramp Installation - 5t Frokift and Crane required | BUFFER | All | 2026-02-07 | 2026-02-07 07:12 | 0.3
A1230 | A0 | Load-out of AGL TR Unit 3; stool down | LOADOUT | All | 2026-02-07 | 2026-02-07 04:48 | 0.2
A1240 | A0 | RoRo ramp removal; Seafastening AGL TR Unit 3 - Crane required | SEAFAST | All | 2026-02-07 | 2026-02-07 | 0
A1250 | A0 | Loading of AGI TR Unit 4 on SPMT; lashing | BUFFER | All | 2026-02-07 | 2026-02-07 | 0
A1260 | A0 | Shifting of AGL TR Unit 4 to Jetty area | BUFFER | All | 2026-02-08 | 2026-02-08 01:12 | 0.05
A1270 | A0 | RoRo Ramp Installation - Crane required | BUFFER | All | 2026-02-08 | 2026-02-08 07:12 | 0.3
A1280 | A0 | Load-out of AGI TR Unit 4; stoold down; securing of SPMT | LOADOUT | All | 2026-02-08 | 2026-02-08 07:12 | 0.3
A1290 | A0 | Removal of RoRo Ramp; Sea fastening AGI TR Unit 4 - Crane required | SEAFAST | All | 2026-02-08 | 2026-02-08 | 0
A1300 | A0 | MWS + MPI + Final Preparations | BUFFER | All | 2026-02-09 | 2026-02-09 04:48 | 0.2
A1310 | A0 | Sail-away - Marine Transportation by LCT to Al Ghallan Island | SAIL | All | 2026-02-10 | 2026-02-10 | 0
A1320 | A0 | LCT Arrival; Berthing at AGL RoRo Jetty | AGI_UNLOAD | All | 2026-02-11 | 2026-02-11 | 0
A1330 | A0 | Unlashing and cutting; steel sets preparations - Forklift required | BUFFER | All | 2026-02-11 | 2026-02-11 | 0
A1340 | A0 | Load-in of AGI TR Unit 4 (including RoRo Ramp Installation); store on Jetty - Crane required | LOADOUT | All | 2026-02-12 | 2026-02-12 | 0
A1350 | A0 | Load-in of AGI TR Unit 3 (including RoRo Ramp Installation); store on Jetty - Crane required | LOADOUT | All | 2026-02-13 | 2026-02-13 | 0
A1360 | A0 | LCT Sails back to MZP to collect TR Units 5-6 (LCT must carry back 4pcs of 7.45m beams) | SAIL | All | 2026-02-14 | 2026-02-14 | 0
A1370 | A0 | Steel bridge Installation 1 - Crane required | BUFFER | All | 2026-02-14 | 2026-02-14 07:12 | 0.3
A1380 | A0 | AGL TR Unit 3 (TR Bay 2) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | BUFFER | All | 2026-02-14 | 2026-02-14 16:48 | 0.7
A1390 | A0 | Turning of AGI TR Unit 3 (TR Bay 2) - 10t Forklift required | TURNING | All | 2026-02-15 | 2026-02-15 | 0
A1400 | A0 | Jacking down of AGI TR Unit 3 (TR Bay 2) on temporary support - Forklift required | JACKDOWN | All | 2026-02-18 | 2026-02-18 | 0
A1410 | A0 | Steel bridge Installation 2 - Crane required | BUFFER | All | 2026-02-18 | 2026-02-18 07:12 | 0.3
A1420 | A0 | AGL TR Unit 4 (TR Bay 1) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | BUFFER | All | 2026-02-18 | 2026-02-18 16:48 | 0.7
A1430 | A0 | Turning of AGI TR Unit 4 (TR Bay 1) - 10t Forklift required | TURNING | All | 2026-02-19 | 2026-02-19 | 0
A1440 | A0 | SPMT shifting back to Port | BUFFER | All | 2026-02-20 | 2026-02-20 | 0
A1450 | A0 | Jacking down of AGI TR Unit 4 (TR Bay 1) on temporary support - Forklift and Crane required | JACKDOWN | All | 2026-02-22 | 2026-02-22 | 0
AGI-011 | A0 | AGI TR Units 5-6 | BUFFER | All | 2026-02-15 | 2026-03-04 | 17
A1460 | A0 | LCT arrives to MZP; Deck preparations | DECK_PREP | All | 2026-02-15 | 2026-02-15 | 0
A1470 | A0 | Loading of AGI TR Unit 5 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | BUFFER | All | 2026-02-16 | 2026-02-16 07:12 | 0.3
A1480 | A0 | RoRo Ramp Installation - 5t Frokift and Crane required | BUFFER | All | 2026-02-16 | 2026-02-16 07:12 | 0.3
A1490 | A0 | Load-out of AGL TR Unit 5; stool down | LOADOUT | All | 2026-02-16 | 2026-02-16 04:48 | 0.2
A1500 | A0 | RoRo ramp removal; Seafastening AGL TR Unit 5 - Crane required | SEAFAST | All | 2026-02-16 | 2026-02-16 | 0
A1510 | A0 | Loading of AGI TR Unit 6 on SPMT; lashing | BUFFER | All | 2026-02-16 | 2026-02-16 | 0
A1520 | A0 | Shifting of AGL TR Unit 6 to Jetty area | BUFFER | All | 2026-02-17 | 2026-02-17 01:12 | 0.05
A1530 | A0 | RoRo Ramp Installation - Crane required | BUFFER | All | 2026-02-17 | 2026-02-17 07:12 | 0.3
A1540 | A0 | Load-out of AGI TR Unit 6; stoold down; securing of SPMT | LOADOUT | All | 2026-02-17 | 2026-02-17 07:12 | 0.3
A1550 | A0 | Removal of RoRo Ramp; Sea fastening AGI TR Unit 6 - Crane required | SEAFAST | All | 2026-02-17 | 2026-02-17 | 0
A1560 | A0 | MWS + MPI + Final Preparations | BUFFER | All | 2026-02-18 | 2026-02-18 04:48 | 0.2
A1570 | A0 | Sail-away - Marine Transportation by LCT to Al Ghallan Island | SAIL | All | 2026-02-19 | 2026-02-19 | 0
A1580 | A0 | LCT Arrival; Berthing at AGL RoRo Jetty | AGI_UNLOAD | All | 2026-02-20 | 2026-02-20 | 0
A1590 | A0 | Unlashing and cutting; steel sets preparations - Forklift required | BUFFER | All | 2026-02-20 | 2026-02-20 | 0
A1600 | A0 | Load-in of AGI TR Unit 6 (including RoRo Ramp Installation); store on Jetty - Crane required | LOADOUT | All | 2026-02-21 | 2026-02-21 | 0
A1610 | A0 | Load-in of AGI TR Unit 5 (including RoRo Ramp Installation); store on Jetty - Crane required | LOADOUT | All | 2026-02-22 | 2026-02-22 | 0
A1620 | A0 | LCT Sails back to MZP to collect TR Unit 7 (LCT must carry back 2pcs of 7.45m beams) | SAIL | All | 2026-02-23 | 2026-02-23 | 0
A1630 | A0 | Steel bridge Installation 1 - Crane required | BUFFER | All | 2026-02-23 | 2026-02-23 07:12 | 0.3
A1640 | A0 | AGL TR Unit 5 (TR Bay 5) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | BUFFER | All | 2026-02-23 | 2026-02-23 16:48 | 0.7
A1650 | A0 | Turning of AGI TR Unit 5 (TR Bay 5) - 10t Forklift required | TURNING | All | 2026-02-24 | 2026-02-24 | 0
A1660 | A0 | Jacking down of AGI TR Unit 5 (TR Bay 5) on temporary support - Forklift required | JACKDOWN | All | 2026-02-27 | 2026-02-27 | 0
A1670 | A0 | Steel bridge Installation 2 - Crane required | BUFFER | All | 2026-02-27 | 2026-02-27 07:12 | 0.3
A1680 | A0 | AGL TR Unit 6 (TR Bay 6) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | BUFFER | All | 2026-02-27 | 2026-02-27 16:48 | 0.7
A1690 | A0 | Turning of AGI TR Unit 6 (TR Bay 6) - 10t Forklift required | TURNING | All | 2026-02-28 | 2026-02-28 | 0
A1700 | A0 | SPMT shifting back to Port | BUFFER | All | 2026-03-01 | 2026-03-01 | 0
A1710 | A0 | Jacking down of AGI TR Unit 6 (TR Bay 6) on temporary support - Forklift and Crane required | JACKDOWN | All | 2026-03-03 | 2026-03-03 | 0
AGI-012 | A0 | AGI TR Unit 7 | BUFFER | All | 2026-02-24 | 2026-03-08 | 12
A1720 | A0 | LCT arrives to MZP; Deck preparations | DECK_PREP | All | 2026-02-24 | 2026-02-24 | 0
A1730 | A0 | Loading of AGI TR Unit 7 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | BUFFER | All | 2026-02-25 | 2026-02-25 07:12 | 0.3
A1740 | A0 | RoRo Ramp Installation - 5t Frokift and Crane required | BUFFER | All | 2026-02-25 | 2026-02-25 07:12 | 0.3
A1750 | A0 | Load-out of AGL TR Unit 7; stool down | LOADOUT | All | 2026-02-25 | 2026-02-25 04:48 | 0.2
A1760 | A0 | RoRo ramp removal; Seafastening AGL TR Unit 7 - Crane required | SEAFAST | All | 2026-02-25 | 2026-02-25 | 0
A1820 | A0 | MWS + MPI + Final Preparations | BUFFER | All | 2026-02-26 | 2026-02-26 | 0
A1830 | A0 | Sail-away - Marine Transportation by LCT to Al Ghallan Island | SAIL | All | 2026-02-27 | 2026-02-27 | 0
A1840 | A0 | LCT Arrival; Berthing at AGL RoRo Jetty | AGI_UNLOAD | All | 2026-02-28 | 2026-02-28 | 0
A1850 | A0 | Unlashing and cutting; steel sets preparations - Forklift required | BUFFER | All | 2026-02-28 | 2026-02-28 | 0
A1860 | A0 | Load-in of AGI TR Unit 7 (including RoRo Ramp Installation); store on Jetty - Crane required | LOADOUT | All | 2026-03-01 | 2026-03-01 | 0
A1890 | A0 | Steel bridge Installation - Crane required | BUFFER | All | 2026-03-02 | 2026-03-02 07:12 | 0.3
A1900 | A0 | AGL TR Unit 7 (TR Bay 7) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | BUFFER | All | 2026-03-02 | 2026-03-02 16:48 | 0.7
A1910 | A0 | Turning of AGI TR Unit 7 (TR Bay 7) - 10t Forklift required | TURNING | All | 2026-03-04 | 2026-03-04 | 0
A1920 | A0 | Jacking down of AGI TR Unit 7 (TR Bay 7) on temporary support - Forklift required | JACKDOWN | All | 2026-03-07 | 2026-03-07 | 0
A1960 | A0 | SPMT shifting back to Port | BUFFER | All | 2026-03-06 | 2026-03-06 | 0
Formulas:
End = [Start]+[Duration]

## Schedule_Data_Option_B
ID | WBS | Task | Phase | Owner | Start | End | Duration | Notes
MOB-001 | A0 | MOBILIZATION | MOBILIZATION | All | 2026-01-26 | 2026-01-30 07:12 | 4.3
SPM-001 | A0 | SPMT | BUFFER | All | 2026-01-26 | 2026-01-26 | 0
MOB-001 | A0 | Mobilization of SPMTs; Asembly + Function Test | MOBILIZATION | All | 2026-01-26 | 2026-01-26 12:00 | 0.5
MAR-002 | A0 | MARINE | BUFFER | All | 2026-01-26 | 2026-01-26 | 0
MOB-001 | A0 | Mobilization of Marine Equipment and Steelworks | MOBILIZATION | All | 2026-01-26 | 2026-01-26 | 0
JAC-003 | A0 | JACKING | BUFFER | All | 2026-01-29 | 2026-01-29 | 0
MOB-001 | A0 | Mobilization of Jacking Equipment, steel bridge, welfare container | MOBILIZATION | All | 2026-01-29 | 2026-02-01 | 3
MOB-001 | A0 | DEMOBILIZATION | MOBILIZATION | All | 2026-03-30 | 2026-04-01 | 2
SPM-004 | A0 | SPMT | BUFFER | All | 2026-03-30 | 2026-03-30 | 0
MOB-001 | A0 | Demobilization of SPMT | MOBILIZATION | All | 2026-03-30 | 2026-03-30 12:00 | 0.5
MAR-005 | A0 | MARINE | BUFFER | All | 2026-03-31 | 2026-03-31 | 0
MOB-001 | A0 | Demobilization of Marine Equipment | MOBILIZATION | All | 2026-03-31 | 2026-03-31 | 0
JAC-006 | A0 | JACKING | BUFFER | All | 2026-03-30 | 2026-03-30 | 0
MOB-001 | A0 | Demobilization of Jacking Equipment, Steel bridge, Welfare Container | MOBILIZATION | All | 2026-03-30 | 2026-03-30 | 0
OPE-007 | A0 | OPERATIONAL | BUFFER | All | 2026-01-27 | 2026-03-30 | 62
BEA-008 | A0 | Beam Replacement | BUFFER | All | 2026-01-27 | 2026-01-29 | 2
BEA-009 | A0 | Beam Replacement AGI TR Unit 1 (TR Bay 4) - Two 5t forklifts required | BUFFER | All | 2026-01-27 | 2026-01-27 | 0
BEA-010 | A0 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required | BUFFER | All | 2026-01-28 | 2026-01-28 | 0
PREP-001 | A0 | Deck Preparations | DECK_PREP | All | 2026-01-27 | 2026-01-29 | 2
PREP-001 | A0 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required | DECK_PREP | All | 2026-01-27 | 2026-01-27 | 0
PREP-001 | A0 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation | DECK_PREP | All | 2026-01-28 | 2026-01-28 | 0
AGI-011 | A0 | AGI TR Units 1-2 | BUFFER | All | 2026-01-29 | 2026-02-14 | 16
LOA-012 | A0 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | BUFFER | All | 2026-01-29 | 2026-01-29 07:12 | 0.3
ROR-013 | A0 | RoRo Ramp Installation - 5t Frokift and Crane required | BUFFER | All | 2026-01-29 | 2026-01-29 07:12 | 0.3
LOA-014 | A0 | Load-out of AGL TR Unit 1; stool down | LOADOUT | All | 2026-01-29 | 2026-01-29 04:48 | 0.2
ROR-015 | A0 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required | SEAFAST | All | 2026-01-29 | 2026-01-29 | 0
LOA-016 | A0 | Loading of AGI TR Unit 2 on SPMT; lashing | BUFFER | All | 2026-01-29 | 2026-01-29 | 0
SHI-017 | A0 | Shifting of AGL TR Unit 2 to Jetty area | BUFFER | All | 2026-01-30 | 2026-01-30 01:12 | 0.05
ROR-018 | A0 | RoRo Ramp Installation - Crane required | BUFFER | All | 2026-01-30 | 2026-01-30 07:12 | 0.3
LOA-019 | A0 | Load-out of AGI TR Unit 2; stoold down; securing of SPMT | LOADOUT | All | 2026-01-30 | 2026-01-30 07:12 | 0.3
REM-020 | A0 | Removal of RoRo Ramp; Sea fastening AGI TR Unit 2 - Crane required | SEAFAST | All | 2026-01-30 | 2026-01-30 | 0
MWS-021 | A0 | MWS + MPI + Final Preparations + Sail-away - Marine Transportation by LCT to Al Ghallan Island | SAIL | All | 2026-01-31 | 2026-01-31 | 0
MMT-022 | A0 | MMT Crew Mob to AGI; Site Induction; Meeting with Client | BUFFER | All | 2026-01-31 | 2026-01-31 | 0
LCT-023 | A0 | LCT Arrival; Berthing at AGL RoRo Jetty | AGI_UNLOAD | All | 2026-02-01 | 2026-02-01 | 0
UNL-024 | A0 | Unlashing and cutting; steel sets preparations - Forklift required | BUFFER | All | 2026-02-01 | 2026-02-01 | 0
LOA-025 | A0 | Load-in of AGI TR Unit 2 (including RoRo Ramp Installation); store on Jetty - Crane required | LOADOUT | All | 2026-02-02 | 2026-02-02 | 0
LOA-026 | A0 | Load-in of AGI TR Unit 1 (including RoRo Ramp Installation); store on Jetty - Crane required | LOADOUT | All | 2026-02-03 | 2026-02-03 | 0
STE-027 | A0 | Steel bridge Installation 1 - Crane required | BUFFER | All | 2026-02-04 | 2026-02-04 07:12 | 0.3
AGL-028 | A0 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | BUFFER | All | 2026-02-04 | 2026-02-04 16:48 | 0.7
TUR-029 | A0 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required | TURNING | All | 2026-02-05 | 2026-02-05 | 0
JAC-030 | A0 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required | JACKDOWN | All | 2026-02-08 | 2026-02-08 | 0
STE-031 | A0 | Steel bridge Installation 2 - Crane required | BUFFER | All | 2026-02-08 | 2026-02-08 07:12 | 0.3
AGL-032 | A0 | AGL TR Unit 2 (TR Bay 3) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | BUFFER | All | 2026-02-08 | 2026-02-08 16:48 | 0.7
TUR-033 | A0 | Turning of AGI TR Unit 2 (TR Bay 3) - 10t Forklift required | TURNING | All | 2026-02-09 | 2026-02-09 | 0
JAC-034 | A0 | Jacking down of AGI TR Unit 2 (TR Bay 3) on temporary support - Forklift and Crane required | JACKDOWN | All | 2026-02-12 | 2026-02-12 | 0
SPM-035 | A0 | SPMT shiifting from TR Bay Area to Jetty; Loading on LCT (if tide allows) | BUFFER | All | 2026-02-11 | 2026-02-11 | 0
MOB-001 | A0 | LCT Sail-away back to Mina Zayed Port; MMT SPMT Crew Demobilization | MOBILIZATION | All | 2026-02-12 | 2026-02-12 | 0
MOB-001 | A0 | MMT Jacking Crew Demobilization | MOBILIZATION | All | 2026-02-13 | 2026-02-13 | 0
AGI-036 | A0 | AGI TR Units 3-4 | BUFFER | All | 2026-02-13 | 2026-03-03 | 18
PREP-001 | A0 | LCT Arrives to MZP; Deck Preparations | DECK_PREP | All | 2026-02-13 | 2026-02-13 | 0
BEA-037 | A0 | Beam Replacement for TR Unit 3 | BUFFER | All | 2026-02-13 | 2026-02-13 | 0
LOA-038 | A0 | Loading of AGI TR Unit 3 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | BUFFER | All | 2026-02-14 | 2026-02-14 07:12 | 0.3
ROR-039 | A0 | RoRo Ramp Installation - 5t Frokift and Crane required | BUFFER | All | 2026-02-14 | 2026-02-14 07:12 | 0.3
LOA-040 | A0 | Load-out of AGL TR Unit 3; stool down | LOADOUT | All | 2026-02-14 | 2026-02-14 04:48 | 0.2
ROR-041 | A0 | RoRo ramp removal; Seafastening AGL TR Unit 3 - Crane required | SEAFAST | All | 2026-02-14 | 2026-02-14 | 0
BEA-042 | A0 | Beam replacement for TR Unit 4 | BUFFER | All | 2026-02-14 | 2026-02-14 16:48 | 0.7
LOA-043 | A0 | Loading of AGI TR Unit 4 on SPMT; lashing | BUFFER | All | 2026-02-15 | 2026-02-15 07:12 | 0.3
SHI-044 | A0 | Shifting of AGL TR Unit 4 to Jetty area | BUFFER | All | 2026-02-15 | 2026-02-15 01:12 | 0.05
ROR-045 | A0 | RoRo Ramp Installation - Crane required | BUFFER | All | 2026-02-15 | 2026-02-15 07:12 | 0.3
LOA-046 | A0 | Load-out of AGI TR Unit 4; stoold down; securing of SPMT | LOADOUT | All | 2026-02-15 | 2026-02-15 07:12 | 0.3
REM-047 | A0 | Removal of RoRo Ramp; Sea fastening AGI TR Unit 4 - Crane required | SEAFAST | All | 2026-02-15 | 2026-02-15 | 0
MWS-048 | A0 | MWS + MPI + Final Preparations + Sail-away - Marine Transportation by LCT to Al Ghallan Island | SAIL | All | 2026-02-17 | 2026-02-17 | 0
MMT-049 | A0 | MMT Crew Mob to AGI; Site Induction; Meeting with Client | BUFFER | All | 2026-02-17 | 2026-02-17 | 0
LCT-050 | A0 | LCT Arrival; Berthing at AGL RoRo Jetty | AGI_UNLOAD | All | 2026-02-18 | 2026-02-18 | 0
UNL-051 | A0 | Unlashing and cutting; steel sets preparations - Forklift required | BUFFER | All | 2026-02-18 | 2026-02-18 | 0
LOA-052 | A0 | Load-in of AGI TR Unit 4 (including RoRo Ramp Installation); store on Jetty - Crane required | LOADOUT | All | 2026-02-19 | 2026-02-19 | 0
LOA-053 | A0 | Load-in of AGI TR Unit 3 (including RoRo Ramp Installation); store on Jetty - Crane required | LOADOUT | All | 2026-02-20 | 2026-02-20 | 0
STE-054 | A0 | Steel bridge Installation 1 - Crane required | BUFFER | All | 2026-02-21 | 2026-02-21 07:12 | 0.3
AGL-055 | A0 | AGL TR Unit 3 (TR Bay 2) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | BUFFER | All | 2026-02-21 | 2026-02-21 16:48 | 0.7
TUR-056 | A0 | Turning of AGI TR Unit 3 (TR Bay 2) - 10t Forklift required | TURNING | All | 2026-02-22 | 2026-02-22 | 0
JAC-057 | A0 | Jacking down of AGI TR Unit 3 (TR Bay 2) on temporary support - Forklift required | JACKDOWN | All | 2026-02-25 | 2026-02-25 | 0
STE-058 | A0 | Steel bridge Installation 2 - Crane required | BUFFER | All | 2026-02-25 | 2026-02-25 07:12 | 0.3
AGL-059 | A0 | AGL TR Unit 4 (TR Bay 1) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | BUFFER | All | 2026-02-25 | 2026-02-25 16:48 | 0.7
TUR-060 | A0 | Turning of AGI TR Unit 4 (TR Bay 1) - 10t Forklift required | TURNING | All | 2026-02-26 | 2026-02-26 | 0
JAC-061 | A0 | Jacking down of AGI TR Unit 4 (TR Bay 1) on temporary support - Forklift and Crane required | JACKDOWN | All | 2026-03-01 | 2026-03-01 | 0
SPM-062 | A0 | SPMT shiifting from TR Bay Area to Jetty; Loading on LCT (if tide allows) | BUFFER | All | 2026-02-28 | 2026-02-28 | 0
MOB-001 | A0 | LCT Sail-away back to Mina Zayed Port; MMT SPMT Crew Demobilization | MOBILIZATION | All | 2026-03-01 | 2026-03-01 | 0
MOB-001 | A0 | MMT Jacking Crew Demobilization | MOBILIZATION | All | 2026-03-02 | 2026-03-02 | 0
AGL-063 | A0 | AGLI TR Units 5-6 | BUFFER | All | 2026-03-02 | 2026-03-20 | 18
PREP-001 | A0 | LCT Arrives to MZP; Deck Preparations | DECK_PREP | All | 2026-03-02 | 2026-03-02 | 0
BEA-064 | A0 | Beam Replacement for TR Unit 5 | BUFFER | All | 2026-03-02 | 2026-03-02 | 0
LOA-065 | A0 | Loading of AGI TR Unit 5 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | BUFFER | All | 2026-03-03 | 2026-03-03 07:12 | 0.3
ROR-066 | A0 | RoRo Ramp Installation - 5t Frokift and Crane required | BUFFER | All | 2026-03-03 | 2026-03-03 07:12 | 0.3
LOA-067 | A0 | Load-out of AGL TR Unit 5; stool down | LOADOUT | All | 2026-03-03 | 2026-03-03 04:48 | 0.2
ROR-068 | A0 | RoRo ramp removal; Seafastening AGL TR Unit 5 - Crane required | SEAFAST | All | 2026-03-03 | 2026-03-03 | 0
BEA-069 | A0 | Beam replacement for TR Unit 6 | BUFFER | All | 2026-03-03 | 2026-03-03 16:48 | 0.7
LOA-070 | A0 | Loading of AGI TR Unit 6 on SPMT; lashing | BUFFER | All | 2026-03-04 | 2026-03-04 07:12 | 0.3
SHI-071 | A0 | Shifting of AGL TR Unit 6 to Jetty area | BUFFER | All | 2026-03-04 | 2026-03-04 01:12 | 0.05
ROR-072 | A0 | RoRo Ramp Installation - Crane required | BUFFER | All | 2026-03-04 | 2026-03-04 07:12 | 0.3
LOA-073 | A0 | Load-out of AGI TR Unit 6; stoold down; securing of SPMT | LOADOUT | All | 2026-03-04 | 2026-03-04 07:12 | 0.3
REM-074 | A0 | Removal of RoRo Ramp; Sea fastening AGI TR Unit 6 - Crane required | SEAFAST | All | 2026-03-04 | 2026-03-04 | 0
MWS-075 | A0 | MWS + MPI + Final Preparations + Sail-away - Marine Transportation by LCT to Al Ghallan Island | SAIL | All | 2026-03-06 | 2026-03-06 | 0
MMT-076 | A0 | MMT Crew Mob to AGI; Site Induction; Meeting with Client | BUFFER | All | 2026-03-06 | 2026-03-06 | 0
LCT-077 | A0 | LCT Arrival; Berthing at AGL RoRo Jetty | AGI_UNLOAD | All | 2026-03-07 | 2026-03-07 | 0
UNL-078 | A0 | Unlashing and cutting; steel sets preparations - Forklift required | BUFFER | All | 2026-03-07 | 2026-03-07 | 0
LOA-079 | A0 | Load-in of AGI TR Unit 6 (including RoRo Ramp Installation); store on Jetty - Crane required | LOADOUT | All | 2026-03-08 | 2026-03-08 | 0
LOA-080 | A0 | Load-in of AGI TR Unit 5 (including RoRo Ramp Installation); store on Jetty - Crane required | LOADOUT | All | 2026-03-09 | 2026-03-09 | 0
STE-081 | A0 | Steel bridge Installation 1 - Crane required | BUFFER | All | 2026-03-10 | 2026-03-10 07:12 | 0.3
AGL-082 | A0 | AGL TR Unit 5 (TR Bay 5) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | BUFFER | All | 2026-03-10 | 2026-03-10 16:48 | 0.7
TUR-083 | A0 | Turning of AGI TR Unit 5 (TR Bay 5) - 10t Forklift required | TURNING | All | 2026-03-11 | 2026-03-11 | 0
JAC-084 | A0 | Jacking down of AGI TR Unit 5 (TR Bay 5) on temporary support - Forklift required | JACKDOWN | All | 2026-03-14 | 2026-03-14 | 0
STE-085 | A0 | Steel bridge Installation 2 - Crane required | BUFFER | All | 2026-03-14 | 2026-03-14 07:12 | 0.3
AGL-086 | A0 | AGL TR Unit 6 (TR Bay 6) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | BUFFER | All | 2026-03-14 | 2026-03-14 16:48 | 0.7
TUR-087 | A0 | Turning of AGI TR Unit 6 (TR Bay 6) - 10t Forklift required | TURNING | All | 2026-03-15 | 2026-03-15 | 0
JAC-088 | A0 | Jacking down of AGI TR Unit 6 (TR Bay 6) on temporary support - Forklift and Crane required | JACKDOWN | All | 2026-03-18 | 2026-03-18 | 0
SPM-089 | A0 | SPMT shiifting from TR Bay Area to Jetty; Loading on LCT (if tide allows) | BUFFER | All | 2026-03-17 | 2026-03-17 | 0
MOB-001 | A0 | LCT Sail-away back to Mina Zayed Port; MMT SPMT Crew Demobilization | MOBILIZATION | All | 2026-03-18 | 2026-03-18 | 0
MOB-001 | A0 | MMT Jacking Crew Demobilization | MOBILIZATION | All | 2026-03-19 | 2026-03-19 | 0
AGL-090 | A0 | AGL TR Unit 7 | BUFFER | All | 2026-03-19 | 2026-03-30 | 11
PREP-001 | A0 | LCT Arrives to MZP; Deck Preparations | DECK_PREP | All | 2026-03-19 | 2026-03-19 | 0
BEA-091 | A0 | Beam Replacement for TR Unit 7 | BUFFER | All | 2026-03-19 | 2026-03-19 | 0
LOA-092 | A0 | Loading of AGI TR Unit 7 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | BUFFER | All | 2026-03-20 | 2026-03-20 07:12 | 0.3
ROR-093 | A0 | RoRo Ramp Installation - 5t Frokift and Crane required | BUFFER | All | 2026-03-20 | 2026-03-20 07:12 | 0.3
LOA-094 | A0 | Load-out of AGL TR Unit 7; stool down | LOADOUT | All | 2026-03-20 | 2026-03-20 04:48 | 0.2
ROR-095 | A0 | RoRo ramp removal; Seafastening AGL TR Unit 7 - Crane required | SEAFAST | All | 2026-03-21 | 2026-03-21 | 0
MWS-096 | A0 | MWS + MPI + Final Preparations + Sail-away - Marine Transportation by LCT to Al Ghallan Island | SAIL | All | 2026-03-22 | 2026-03-22 | 0
MMT-097 | A0 | MMT Crew Mob to AGI; Site Induction; Meeting with Client | BUFFER | All | 2026-03-22 | 2026-03-22 | 0
LCT-098 | A0 | LCT Arrival; Berthing at AGL RoRo Jetty | AGI_UNLOAD | All | 2026-03-23 | 2026-03-23 | 0
UNL-099 | A0 | Unlashing and cutting; steel sets preparations - Forklift required | BUFFER | All | 2026-03-23 | 2026-03-23 | 0
LOA-100 | A0 | Load-in of AGI TR Unit 7 (including RoRo Ramp Installation); store on Jetty - Crane required | LOADOUT | All | 2026-03-24 | 2026-03-24 | 0
STE-101 | A0 | Steel bridge Installation 1 - Crane required | BUFFER | All | 2026-03-25 | 2026-03-25 07:12 | 0.3
AGL-102 | A0 | AGL TR Unit 7 (TR Bay 7) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | BUFFER | All | 2026-03-25 | 2026-03-25 16:48 | 0.7
TUR-103 | A0 | Turning of AGI TR Unit 7 (TR Bay 7) - 10t Forklift required | TURNING | All | 2026-03-26 | 2026-03-26 | 0
JAC-104 | A0 | Jacking down of AGI TR Unit 7 (TR Bay 7) on temporary support - Forklift required | JACKDOWN | All | 2026-03-29 | 2026-03-29 | 0
Formulas:
End = [Start]+[Duration]